DAY5
SESSION ASSIGNMENTS

1.What is a story point? How will you use story points to measure size of the following fruits (fruit points) given the planning poker value ½, 1, 2, 3, 5,8,13, 20, 40, 100, infinity

Apple
Mango
Banana
Jack fruit
Pine
apple
Gooseberry
Avocado
Lime
Pomegranate
Watermelon

soln: Story point is an estimate time given to complete a user story. It is alloted as a point to a particular story.This is used to measure the effort required to implement a story. This can also be based on the difficulty to do a task ie, it tells how much complecated the story is.
The poker values can be assigned as follows:
Gooseberry - 1/2
lime - 1
avacado - 2
apple - 3
pomegranite - 5
mango - 8
banana - 13
pine apple - 20
watermelon - 40
jackfruit - 100

2. What are the points discussed during the daily standup meeting? What happens if there is a problem a team member identifies during the stand up meeting and how the same will be resolved?
Soln: Daily standup meetings should be conducted every morning and should last upto a maxcimum of 15 minutes. The main objective of it is to improve the communications within the team and also to promote transparency and commitment. The main points discussed during a standup meeting are
- what have i done so far ?
- What am i going to do until the next meeting?
- Do i have impediments ?
The stand up meeting also ensures that fast dicisions are made.
If a team member identifies a problem during the standup meeting it will not be resolved during that standup meeting, but an alternate meeting will be organized with that individual and the problem will be resolved. If multiple people are related to that problem they will also be included in that meeting.

3.What is the relationship between Epic, User story and Feature? What are themes?

Soln:	Basically the user story is what the user wants. It is a very high-level definition of a requirement, containing just enough information so that the developers can analyze and implement it. A user story is one or more sentences what the user wants to achieve. A user story will be written from the requirements of the customer.The product owner is the one representing the customer, he knows all the requirements the customer wants. He is the person interacting with the customer and analyzing the features of the product the client wants.
An epic is a large user story. This story will be able to broken into smaller user stories. But there is no guarantee that all will be developed or released.
A feature is distinguishing characteristic or capability of a software application or library. This will be a unique functionality of the software. There will be multiple features for the software.
A theme is a collection of user stories. From the product backlog we can take a collection of the user stories, which can be collectively called themes.

4.Provide an example of Feature and user stories for the below Epic:
Epic: Allow the customers to manage their own accounts in the web portal

soln: in the below epic
Feature:	Customers will be having their profiles and they can
Edit their profile

User story:	As a Customer I would like to access details so that I can check whether my	information is correct.
As a Customer I would like to edit profile so that I can correct information if	it is not correct or update additional details.
5. Estimate

Product backlog item	Estimate
Read a high-level, 10-page overview of agile software development in a celebrity magazine.	1
Read a densely written 5-page research paper about agile software development in an academic journal.	2
Write the product backlog for a simple eCommerce site that sells only clocks.	1/2
Recruit, interview, and hire a new member for your team.	3
Create a 60-minute presentation about agile estimating and planning for your coworkers.	2
Wash and wax your boss’ Porsche.	1
Read a 150-page book on agile software development.	2
Write an 8-page description of agile development for your boss	2